Scope of Work – Group

Group Members: Savanna Flores, Nathan Jones, Gavin Rothmeyer, Kruvel Worku

Date Submitted for Review: April 21, 2026

Submitted to: Civil and Environmental Engineering Department Faculty

Project Goals:

The purpose of this project is to conduct a natural disaster risk analysis for two states using the FEMA National Risk Index (NRI) data and the CDC/ATSDR Social Vulnerability Index (SVI) Risk Averse, LLC has tasked the team with performing analysis to evaluate bias in the NRI method by applying and comparing the consultant developed risk method. Comparison of the results will highlight differences in risk identification and the effects on a community. All client specific requirements will be addressed upon completion of this project. The two states selected include Iowa and Nebraska. Sources that are relevant for data analysis include National Centers for Environmental Information, and U.S. Census Bureau.  All analysis will be done within a Jupyter Notebook, an annotated code document, a GitHub repository, an engineering timesheet, and a detailed technical report.

Task 1: Analyze Data

The NRI CSV and Metadata files will be downloaded from the FEMA data site for Iowa and Nebraska. The corresponding SVI data will be downloaded from the ATSDR site. The data will be interpreted to find missing values and understand what is required for merging. The metadata will be used for a clean understanding of the information and overall creates a foundation of understanding for further analysis. The NRI definition of risk is the likelihood of a natural hazard occurring and its consequences on the surrounding environment. The NRI calculates this using three components: Expected Annual Loss, Social Vulnerability, and Community Resilience. This gives every community a risk index score to rank against other communities geographically.

Task 2: Python Code

A structured Jupyter Notebook (.ipynb) will organize imported data, analysis, combining NRI and SVI data, filling missing values, applying risk analysis from both NRI and consultant methods, and graphic visuals. Risk index scores will be calculated using the NRI formula: Risk Index = Expected Annual Loss * Social VulnerabilityCommunity Resilience and using an alternatively developed risk scoring method for comparison. The notebook will include summary tables and figures that compare the calculated risk scores from each method and use GeoPandas to display the risk information on a map.

Task 3: Documentation and Reporting

A Jupyter Notebook (.ipynb) that presents the code structure and sequential prompts will be created. Attached will also be an Annotated Code Document, which will describe all Excel-to-Python logic through detailed individual line-by-line explanations. The technical report will include an Introduction, explain the Methods, analyze and discuss Results, and a References section. Additionally, a GitHub repository will store all code, documentation, and a README file containing User Guide information. Lastly, a Gantt Chart will display task sequences, task durations, and all project milestones.

Table 1: Final Deliverables

| Deliverable | Files Included | Date |
| --- | --- | --- |
| Raw Data File | CIVE202_Spring2025_ Group_Project4_Raw | 4/21/26 |
| Python Code | CIVE202_Spring2025_ Group_Project4_Code.ipynb | 4/21/26 |
| Organized Files | GitHub Link containing this data | 4/21/26 |
| Scope of Work | CIVE202_Spring2025_ Group_Project4_SOW.DOCX | 4/21/26 |
| Annotated Code | CIVE202_Spring2025_ Group_Project4_ACD.DOCX | 4/21/26 |
| Written Report | CIVE202_Spring2025_Group_Project4_Report.DOCX | 4/21/26 |

References

National Centers for Environmental Information. (2025). Billion-dollar weather and climate disasters. National Oceanic and Atmospheric Administration. https://www.ncei.noaa.gov/access/billions/

U.S. Census Bureau. (2025). American Community Survey (ACS). United States Census Bureau. https://www.census.gov/programs-surveys/acs